## Matrix
ID | Need | Source | Requirement | Priority | Owner | Acceptance evidence | Status | Decision note | In conflict | Must, with no acceptance evidence
Stable identifier, never reused | The business problem, in the words of the person who has it | Who said it, where and when (interview, workshop, document) | What the system must do, testable | Must, Should, Could or Won't | The person who accepts it as met | What will be shown to prove it works | Proposed, Agreed, In conflict, Rejected or Changed | Why it was agreed, rejected or changed, and by whom

## Worked example
Illustrative: a CRM replacement at a made-up company.
ID | Need | Source | Requirement | Priority | Owner | Acceptance evidence | Status | Decision note
R-01 | Sales managers cannot see which deals are stuck | Sales director interview, 3 Mar | Show deals with no activity for 14 days on the pipeline view | Must | Sales director | Demo on migrated data: stuck deals flagged correctly for one region | Agreed
R-02 | Finance re-keys every won deal into the billing system | Finance workshop, 5 Mar | Send won deals to billing with customer, price and terms | Must | Finance manager | Ten test deals reach billing with no manual entry | Agreed
R-03 | Reps want to log calls from their phones | Rep survey, 7 Mar | Log a call from the mobile app in under 30 seconds | Should | Sales operations lead | Five reps log a call on their own phones, timed | Agreed
R-04 | Discounts over 15% get approved by email and lost | Sales director interview, 3 Mar | Discounts over 15% need approval in the system | Must | Sales director | A 20% discount cannot be sent without approval | In conflict | Finance says the limit should be 10% (workshop, 5 Mar). Sales director and finance manager to settle before build.
R-05 | Marketing wants a lead score on every contact | Marketing lead email, 8 Mar | Score every contact from 0 to 100 | Could | Marketing lead |  | Rejected | No agreed scoring model and no one to maintain it. Rejected by the sponsor, 12 Mar; revisit after go-live.
R-06 | Customer success cannot see what was promised in the sale | Customer success interview, 6 Mar | Show the signed order form and handoff notes on the account | Must | Head of customer success | Handoff notes visible on three migrated accounts | Agreed

## How to use
How to use this matrix
1. One row per need. Record the need in the words of the person who has it, and where you heard it.
2. Turn each need into a requirement someone could test. If you cannot say how it would be tested,
it is not a requirement yet.
3. Give every requirement an owner who will accept it, and the evidence they will accept.
4. When two people want different things, mark both rows In conflict and name who settles it.
Do not average them.
5. Keep rejected rows, with the reason and who decided. They stop the same request coming back.
From: Requirements traceability matrix template, autospark.ai