## Handoff
Commitment | Where it was promised | In the contract? | Owner after handoff | How we will know it is delivered | Receiving team's answer | Open question | Commitments outside the contract | Not yet accepted
What the customer was told they would get, in their words where possible | Contract clause, proposal page, email or call, with a date | Yes or No. A No is not wrong, but it must be visible | A named person, not a team | What the customer would accept as done | Accepted, Queried or Cannot deliver | What still has to be settled, and with whom

## Worked example
Illustrative. It describes no real client or deal.
Commitment | Where it was promised | In the contract? | Owner after handoff | How we will know it is delivered | Receiving team's answer | Open question
Go live on the new platform by 1 March | Order form, clause 4 | Yes | Implementation lead | Users log in and process a live order | Accepted
Migrate three years of order history | Proposal, page 6 | Yes | Data engineer | Customer signs off a sample of 50 migrated orders | Queried | Proposal says three years; the data export only holds two. Confirm with the customer before kickoff.
Weekly check-in for the first eight weeks | Discovery call, 14 Jan | No | Customer success manager | Eight calls held and minuted | Accepted
A custom margin report by month one | Email from the account executive, 22 Jan | No | Customer success manager | Report agreed with the finance director | Cannot deliver | Not in scope or price. Agree with the customer what replaces it before the kickoff call.
Single sign-on with their identity provider | Order form, clause 7 | Yes | Implementation lead | Staff sign in with their company login | Accepted
Named escalation contact | Proposal, page 9 | Yes | Head of customer success | Contact named in the kickoff pack | Accepted

## How to use
How to use this template
1. Before the handoff meeting, the seller lists every commitment the customer heard: from the
contract, the proposal, emails and calls. Promises made outside the contract belong here most.
2. For each, record where it was promised and whether it is in the contract.
3. The receiving team names an owner and says what 'delivered' means to the customer.
4. The receiving team answers every row: Accepted, Queried or Cannot deliver.
5. The handoff is complete when no row is Queried and every Cannot deliver has an agreed
replacement that has been discussed with the customer.
From: Sales to customer success handoff template, autospark.ai